## WELCOME PAGE
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Welcome Page |  |  |  |  | COMPANY NAME | [6 empty] | HIFI IT PARK
PROJECT MANAGER |  | HAREESH |  |  |  |  | DATE | [6 empty] | 2024-10-19
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | Header | CLINTON | 20/05/2025 | 20/05/2025 | 5 HOURS | PROCESS | bar: WEEK 1 M to WEEK 1 W
1.2 | Trend Page | FAZITH | 20/05/2025 | 20/05/2025 | 5 HOURS | PROCESS | bar: WEEK 1 M to WEEK 1 W
1.3 | IT Service Section | LINGA KUMAR | 20/05/2025 | 20/05/2025 | 5 HOURS | PROCESS | bar: WEEK 1 M to WEEK 1 W
1.4 | Automation Section |  |  |  | 0
1.5 | HRMS |  |  |  | 0
1.6 | Academy |  |  |  | 0
1.7 | FMCG |  |  |  | 0
1.8 | Terms & conditions |  |  |  | 0
1.9 | Footer |  |  |  | 0

## STORE
GANTT CHART TEMPLATE | [10 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE | [5 empty] | IT PARK - STORE |  |  |  |  | COMPANY NAME | [6 empty] | HIFI IT PARK
PROJECT MANAGER | [5 empty] | HAREESH |  |  |  |  | DATE | [6 empty] | 2024-10-19
Project End Date : 02/12/24 | [10 empty] | Remaning Pending Works : Rescheduling for Adding Extra features As per Sir Advise.
WBS NUMBER | TASK TITLE |  |  |  |  | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  | Front End | Name | Completed By Employee ID | Back End | [5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[11 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Home Page
1.1 | Header with navbars &dropdown | Completed | Priya | HIFI - F040 | Completed |  |  |  | 0 | 0%
1.2 | Product Filter Concept | Completed | Priya | HIFI - F040 | InComplete | Valli | 2024-10-23 | 2024-10-29 | 6 | 100% | bar: WEEK 1 W to WEEK 2 W
1.3 | ImageSlider | Completed | Priya | HIFI - F040 | - |  |  |  | 0 | 0%
1.4 | Trending offers | Completed | Murugavalli | HIFI - F019 | Completed |  |  |  |  | 0%
1.5 | Viewproduct list (all products) | Completed | Priya | HIFI - F040 | Completed |  |  |  | 0 | 0%
1.6 | Cart count add to carticon | Completed | Murugavalli | HIFI - F019 | Completed |  |  |  |  | 0%
1.7 | Footer | Completed | Murugavalli | HIFI - F019 | - |  |  |  |  | 0%
1.8 | Store Home Page | Completed | Murugavalli | HIFI - F019 | InComplete | Gowtham | 2024-11-09 | 2024-11-11 | 2 | 100%
1.9 | FMCG Home Page | On Progress | Murugavalli | HIFI - F019 | Completed | Gowtham | 2024-11-11 | 2024-11-12 | 1 | 100%
1.1 | Automation Home Page | Completed | Murugavalli | HIFI - F019 | InComplete | Murugavalli | 2024-11-09 | 2024-11-11 | 2 | 100%
1.11 | IT-Products Home Page | On Progress | Priya | HIFI - F040 | InComplete | Gowtham | 2024-11-13 | 2024-11-16 | 3 | 100%
1.12 | Academy Home Page | On Progress | Murugavalli | HIFI - F019 | InComplete | Murugavalli | 2024-12-04 | 2024-12-09 | 5 | 100%
1.13 | HRMS Home Page | On Progress | Priya | HIFI - F019 | InComplete | Gowtham | 2024-12-17 | 2024-12-17 | 0 | 0%
2 | Filter Pages
2.1 | Combo Offers page | Completed | Murugavalli | HIFI - F019 | Completed |  |  |  | 0 | 0%
2.2 | whislistist product page view | Completed | Priya | HIFI - F040 | Completed |  |  |  | 0 | 0%
2.3 | AddtoCart product page view | Completed | Murugavalli | HIFI - F019 | Completed |  |  |  | 0 | 0%
2.4 | Under Construction | Completed | Gowtham | HIFI - F036 | - |  |  |  | 0 | 0%
2.5 | About Us | Completed | Murugavalli | HIFI - F019 | - |  |  |  | 0 | 0%
2.6 | Contact Us | Completed | Murugavalli | HIFI - F019 | Completed |  |  |  | 0 | 0%
2.7 | Order confiirm page | incompleted | Murugavalli | HIFI - F019 |  | Valli | 2024-11-06 | 2024-11-12 | 6 | 100%
2.8 | ViewProduct Updated Version | On Progress | Gowthem | HIFI - F036 | On Progress | Gowthem | 2024-12-31 | 2025-01-04 | 4 | 0%
2.9 | Filter Products View Page | On Progress | Gowthem | HIFI - F036 | On Progress | Gowthem | 2024-12-25 | 2025-01-01 | 6 | 0%
2.1 | Order confiirm page | Completed | Gowthem | HIFI - F036 | Completed | Gowthem | 2025-01-06 | 2025-01-10 | 4 | 0%
3 | Address
3.1 | ShippingAddress page | Completed | Murugavalli | HIFI - F019 | Completed |  |  |  | 0 | 0%
3.2 | Edit Address page | Completed | Priya | HIFI - F040 | Completed |  |  |  | 0 | 0%
3.3 | Add Address page | Completed | Priya | HIFI - F040 | Completed |  |  |  | 0 | 0%
3.2 | Saved Multiple Address page | Completed | Priya | HIFI - F040 | Completed |  |  |  | 0 | 0%
4 | Payment
4.1 | payment page | Completed | Priya | HIFI - F040 | InComplete | Valli | 2024-10-30 | 2024-11-05 | 5 | 100% | bar: WEEK 2 F to WEEK 3 R
4.2 | Order Page | Completed | Priya | HIFI - F040 | Completed | Priya | 2024-10-21 | 2024-10-23 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
4.3 | Place Order confiirm page | Completed | Murugavalli | HIFI - F019 | InComplete | Valli | 2024-11-17 | 2024-11-20 | 3 | 100%
4.4 | Cash on Delivery | Completed | Completed | Completed | Completed | Priya
4.5 | Online Payment | Completed | Completed | Completed | InComplete | Valli | 2024-12-12 | 2024-12-16 | 4 | 100%
5 | Footer
5.1 | Product | [7 empty] | 0 | 0%
5.1.1 | ShippingPolicy | Completed | Priya | HIFI - F040 | - |  |  |  | 0 | 0%
5.1.2 | Terms & Conditions | Completed | Priya | HIFI - F040 | - |  |  |  | 0 | 0%
5.1.3 | Refunds & Replacement | Completed | Priya | HIFI - F040 | - |  |  |  | 0 | 0%
5.1.4 | Privacy Policy | Completed | Priya | HIFI - F040 | - |  |  |  | 0 | 0%
5.2 | For Business | [7 empty] | 0 | 0%
5.2.1 | Feedback | Completed | Murugavalli | HIFI - F019 | InComplete | Priya | 2024-12-10 | 2024-12-17 | 7 | 0%
5.2.2 | Testimonials | Completed | Murugavalli | HIFI - F019 | - |  |  |  | 0 | 0%
5.2.3 | Blogs | Completed | Murugavalli | HIFI - F019 | - |  |  |  | 0 | 0%
5.2.4 | CaseStudies | Completed | Murugavalli | HIFI - F019 | - |  |  |  | 0 | 0%
4 | Login Page
4.1 | Login | Completed | Mathan | HIFI - F025 | Completed | Gowtham | 2024-10-23 | 2024-11-05 | 12 | 100% | bar: WEEK 1 T to WEEK 3 M
4.3 | SignUp With OTP | Completed | Mathan | HIFI - F025 | Completed | Gowtham | 2024-10-18 | 2024-10-22 | 4 | 100% | bar: WEEK 1 F to WEEK 2 W
4.4 | ForgotPassword | Completed | Mathan | HIFI - F025 | Completed | Gowtham | 2024-11-07 | 2024-11-11 | 4 | 100%
4.4 | OTP & Reset OTP | Completed | Mathan | HIFI - F025 | Completed | Gowtham | 2024-11-12 | 2024-11-14 | 2 | 100%
4.5 | New Password | Completed | Mathan | HIFI - F025 | Completed | Gowtham | 2024-11-15 | 2024-11-19 | 4 | 100%
4.6 | Change Password | Completed | Mathan | HIFI - F025 | Completed | Gowtham | 2024-11-20 | 2024-11-22 | 2 | 100%

## HRMS
GANTT CHART TEMPLATE | [11 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE | [6 empty] | IT PARK - HRMS |  |  |  |  | COMPANY NAME | [6 empty] | HIFI IT PARK
PROJECT MANAGER | [6 empty] | HAREESH |  |  |  |  | DATE | [6 empty] | 2024-10-19
Project End Date : 28/02/25
WBS NUMBER | TASK TITLE |  |  |  | PCT OF TASK COMPLETE |  | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  | Front End | Name | Complted By Employee ID |  | Back End | [5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[12 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | COMMON PAGES
1.1 | Home Page | Completed | Arun | HIFI - F020 | 100% | Completed |  |  |  | 0 | 0%
1.2 | Login | Completed | Arun | HIFI - F020 | 100% | In Completed | Arun,Usha,Kathir | 2024-10-28 | 2024-11-05 | 7 | 80% | bar: WEEK 1 M to WEEK 2 T
1.3 | Signup | Completed | Usha | HIFI - F016 | 100% | Completed |  |  |  | 0 | 0%
1.4 | Careers | Completed | Kathir | HIFI - F026 | 100% | Completed |  |  |  | 0 | 0%
1.5 | About Us | Completed | Usha | HIFI - F016 | 100% | Completed |  |  |  | 0 | 0%
1.6 | Contact Us | Completed | Usha | HIFI - F016 | 100% | Completed |  |  |  | 0 | 0%
1.8 | Forgot | Completed | Kathir | HIFI - F026 | 100% | In Completed | Kathir | 2024-11-06 | 2024-11-11 | 5 | 100%
1.9 | OTP & Resend OTP | Completed | Kathir | HIFI - F026 | 100% | In Completed | Usha | 2024-11-06 | 2024-11-11 | 5 | 100%
1.1.0 | Change Password | Completed | Arun | HIFI - F020 | 100% | In Completed | Kathir | 2024-11-06 | 2024-11-11 | 5 | 100%
1.11 | New Password | Completed | Arun | HIFI - F020 | 100% | In Completed |  |  |  | 0 | 0%
1.12 | Choose User Type | Completed | Katrhir | HIFI - F026 | 100% | In Completed | Arun | 2024-11-06 | 2024-11-11 | 5 | 100% | bar: WEEK 2 W to WEEK 3 T
2 | CANDIDATE
2.1 | Candidate Registration | Completed | Arun | HIFI - F020 | 100% | In Completed | usha | 2024-12-04 | 2024-12-10 | 6 | 80%
2.2 | Welcome Page for Candidate | Completed | Arun | HIFI - F020 | 100% | Completed |  |  |  | 0 | 0%
2.3 | Candidate DashBoard | Completed | Arun | HIFI - F020 | 100% | In Completed | Arun | 2024-12-04 | 2024-12-10 | 6 | 100%
2.4 | Candidate Job | Completed | Arun | HIFI - F020 | 100% | In Completed | Arun | 2024-12-12 | 2024-12-18 | 6 | 100%
2.5 | Candidate Job Details | Completed | Arun | HIFI - F020 | 100% | In Completed | Arun | 2024-12-19 | 2024-12-25 | 6 | 100%
2.6 | Candidate Profile | Completed | Arun | HIFI - F020 | 100% | In Completed | Arun | 2024-12-26 | 2025-01-02 | 6 | 0%
2.7 | Candidate Feedback | Completed | Arun | HIFI - F020 | 100% | In Completed | Arun | 2025-01-02 | 2025-01-08 | 6 | 0%
3 | ADMIN
3.1 | Admin Dashboard | Completed | Usha | HIFI - F016 | 100% | In Completed | Usha | 2024-12-05 | 2024-12-11 | 6 | 100%
3.2 | Applied Jobs(admin) | Completed | Usha | HIFI - F016 | 100% | In Completed | Usha | 2024-12-12 | 2024-12-18 | 6 | 100%
3.3 | Client Database(admin) | Completed | Usha | HIFI - F016 | 100% | In Completed | Usha | 2024-12-19 | 2024-12-25 | 6 | 0%
3.4 | Candidate Database(admin) | Completed | Usha | HIFI - F016 | 100% | In Completed | Usha | 2024-12-26 | 2025-01-02 | 6 | 0%
3.5 | View JobDetails(admin) | Completed | Usha | HIFI - F016 | 100% | In Completed | Usha | 2025-01-02 | 2025-01-08 | 6 | 0%
4 | CLIENT
4.1 | Company Details(Client) | Completed | Katrhir | HIFI - F026 | 100% | Completed | Usha | 2024-11-26 | 2024-12-04 | 8 | 100%
4.2 | Hr Details(Client) | Completed | Katrhir | HIFI - F026 | 100% | In Completed | Arun,Usha,Kathir | 2024-11-28 | 2024-11-30 | 2 | 100%
4.3 | Hiring Details(Client) | Completed | Katrhir | HIFI - F026 | 100% | Completed | Kathir | 2024-11-26 | 2024-11-30 | 4 | 100%
4.4 | Welcome Page for Client | Completed | Katrhir | HIFI - F026 | 100% | In Completed | Kathir | 2024-12-05 | 2024-12-13 | 8 | 100%
4.5 | Client DashBoard | Completed | Arun | HIFI - F020 | 100% | Completed | Arun | 2024-11-26 | 2024-11-30 | 4 | 100%
4.6 | Client Profile | Completed | Katrhir | HIFI - F026 | 100% | In Completed | Kathir | 2024-12-24 | 2024-12-31 | 7 | 0%
4.7 | Client Feedback | Completed | Katrhir | HIFI - F026 | 100% | In Completed | Kathir | 2025-01-02 | 2025-01-08 | 6 | 0%
5 | HR
5.1 | HR Dashboard | Completed | Arun | HIFI - F020 | 100% | In Completed | Arun | 2025-01-09 | 2025-01-24 | 15 | 0%
5.2 | HR Candidate Database | Completed | Arun | HIFI - F020 | 100% | In Completed | Kathir | 2025-01-09 | 2025-01-24 | 15 | 0%
5.3 | HR Client Database | Completed | Arun | HIFI - F020 | 100% | In Completed | Kathir | 2025-01-25 | 2025-02-06 | 11 | 0%
5.4 | View JobDetails(HR) | Completed | Usha | HIFI - F016 | 100% | In Completed | Usha | 2025-01-09 | 2025-01-24 | 15 | 0%
5.5 | Applied Jobs(HR) | Completed | Usha | HIFI - F016 | 100% | In Completed | Usha | 2025-01-25 | 2025-02-06 | 11 | 0%
5.6 | Candidate JobDetails(HR) | Completed | Usha | HIFI - F016 | 100% | In Completed | Arun | 2025-01-25 | 2025-02-06 | 11 | 0%
6 | HR & Admin Login | Completed | Arun,Usha,Kathir | HIFI - F020,HIFI - F016,HIFI - F026 | 100% | In Completed | Arun,Usha,Kathir | 2025-02-07 | 2025-02-28 | 21 | 0%

## viens hrms
GANTT CHART TEMPLATE | [11 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE | [6 empty] | Vienstereoptic - HRMS |  |  |  |  | COMPANY NAME | [6 empty] | HIFI IT PARK
PROJECT MANAGER | [6 empty] | Parthi Raja |  |  |  |  | DATE | [6 empty] | 2024-10-19
Project End Date : 28/02/25
WBS NUMBER | TASK TITLE |  |  |  | PCT OF TASK COMPLETE |  | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
|  | Front End | Name | Complted By Employee ID |  | Back End | [5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[12 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | COMMON PAGES
1.1 | Home Page | Completed | Sariga
1.2 | Login | Completed | Dhamu |  |  | Dhamu | bar: WEEK 1 M to WEEK 2 T
1.3 | Signup | Completed | Dhamu |  |  | Dhamu
1.4 | Careers | Completed | Clinton |  |  | Sariga
1.5 | About Us | Completed | Fazith
1.6 | Contact Us | Completed | Linga |  |  | Linga
1.8 | Forgot | Completed | Clinton |  |  | Clinton
1.9 | OTP & Resend OTP | Completed | Dhamu |  |  | Dhamu
1.1.0 | Change Password | Completed | Sariga |  |  | Sariga
1.11 | New Password | Completed | Dhamu |  |  | Dhamu
1.12 | Choose User Type | Completed | Linga |  |  | Linga | bar: WEEK 2 W to WEEK 3 T
2 | CANDIDATE
2.1 | Candidate Registration | Completed | Sariga |  |  | Sariga
2.2 | Welcome Page for Candidate | Completed | Sariga
2.3 | cadidate dashboard | Completed | Sariga
2.4 | cadidate job | Completed | Sariga |  |  | Sariga
2.5 | Candidate Job Details | Completed | Dhamu |  |  | Dhamu
2.6 | Candidate Profile | Completed | Dhamu |  |  | Dhamu | bar: WEEK 1 F; WEEK 4 F; WEEK 7 F; WEEK 10 F
2.7 | candidate feedback | Completed | Dhamu |  |  | Dhamu | bar: WEEK 1 F; WEEK 4 F; WEEK 7 F; WEEK 10 F
3 | ADMIN
3.1 | Admin Dashboard | Completed | Linga
3.2 | Applied Jobs(admin) | Completed | Fazith |  |  | Linga
3.3 | Client Database(admin) | Completed | Clinton |  |  | Linga
3.4 | Candidate Database(admin) | Completed | Dhamu |  |  | Clinton
3.5 | View JobDetails(admin) | Completed | Sariga |  |  | Dhamu
4 | CLIENT
4.1 | Dashboard (Client) | Completed | Clinton |  |  | Clinton
4.2 | Add Jobs (Client) | Completed | Fazith |  |  | Fazith
4.3 | Add HR (Client) | Completed | Linga |  |  | Linga
4.4 | Welcome Page for Client | Completed | Fazith
4.5 | Notifications | Completed | Clinton |  |  | Clinton
4.6 | Interview | Completed | Clinton |  |  | Clinton
4.7 | onboard | Completed | Clinton |  |  | Clinton
4.8 | Client Profile | Completed | Linga |  |  | Linga
4.9 | Logout | Completed | Fazith |  |  | Fazith
4.1 | client feedback | Completed | Fazith |  |  | Fazith
5 | HR
5.1 | HR Dashboard | Completed | Linga
5.2 | HR Candidate Database | Completed | Fazith |  |  | Fazith
5.3 | HR Client Database | Completed | Clinton |  |  | Clinton
5.4 | View JobDetails(HR) | Completed | Sariga |  |  | Sariga
5.5 | Applied Jobs(HR) | Completed | Dhamu |  |  | Dhamu
5.6 | interview | Completed | Dhamu |  |  | Dhamu
5.7 | onboard | Completed | Dhamu |  |  | Dhamu
5.8 | Candidate JobDetails(HR) | Completed | Dhamu |  |  | Dhamu
6 | HR & Admin Login | Incomplete | Sariga |  |  | Sariga